## Sheet1
PLAN
2017-01-30 | 2017-02-06 | 2017-02-13 | 2017-02-20 | 2017-02-27 | 2017-03-06 | 2017-03-13 | 2017-03-20 | 2017-03-27 | 2017-04-03 | 2017-04-10 | 2017-04-17 | 2017-04-24 | 2017-05-01 | 2017-05-08 | 2017-05-15 | 2017-05-22
Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 |  |  |  | Week 12 | Week 13 | Week 14
SpreadSheet | Presentation | Background Creation | finish delvirables for CW1 | Program Movement | Program First Enemy AI | Program Attack | Program Health | Program Pickups/ Ammo Types | Program Boss | Program Second Enemy AI & Attack |  |  |  | Projectile program | Debug/ Testing | Additional Needs
Game Design Document | Background Concept | Room Design | Room Intergration | Enemies | Program Animation for Enemy | Program First Enemy AI | Program Enemy Attack | Room Creation Lobby | Projectile Design | Projectile intergration |  |  |  | Ammo Change
| Enemies Concept |  | Character Concept | Character | Movement Animation for Character | Movement Animation for Character | boss Room |  | Projectile Creation | Program Animation for Character |  |  |  | UI
[5 empty] | Movement Animation for Enemy | Movement Animation for Enemy |  |  | Boss Concept | Boss
Actual
2017-01-30 | 2017-02-06 | 2017-02-13 | 2017-02-20 | 2017-02-27 | 2017-03-06 | 2017-03-13 | 2017-03-20 | 2017-03-27 | 2017-04-03 | 2017-04-10 | 2017-04-17 | 2017-04-24 | 2017-05-01 | 2017-05-08 | 2017-05-15 | 2017-05-22
Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 |  |  |  | Week 12 | Week 13 | Week 14
As a developer I want a SpreadSheet because I want to see what needs to be done each sprint | As a Investor I want a Presentation because I want to understand the concept of the game | As a visionary I want Background Creation because I want to see my idea becoming real | As an Investor I want finished delvirables for CW1 because then I can review the idea | As a Player I want a character because I want to see who I'm controlling | As a player I want to attack because I need to be able to kill the enemies | As a player I want the enemy to attack me because the game would have no challenge without it | As a Designer I want a place for the boss so I created a boss room | As a designer I want the game to be challenging so I created a boss from the concept | As a programer I wanted to create a challanging boss so I gave him different phases | As a programer I noticed bugs in the program that I wanted to fix so that the users experience was better |  |  |  | As an Investor I want the product that was described so the programed version and design version were merged | As a Player I want the game to have a UI so that I can see whats going on in the game | As a programer I want to debug and test the game before launch so that the game is as high a quality as It can be
As an invester I want a Game Design Document because it makes the concept of the game clear | As a visionary I want a Background Concept because it will allow me to see my game being created | As a developer I want Room Design because I need to know what I'm working with | As a developer I want Room Intergration because I can then begin programing | As a player I want Enemies because I need a goal within the game | As a player I want health so that the enemy can kill me | As a designer I want the game to be challanging so I created a concept for a boss enemy | As a Visonary I wanted multiple ammo types so that there was more strategy in the game | As a visonary I wanted limited ammo of each type so pickups were required | As a designer I created projectiles from the design so that the boss had something to fire | As a designer I wanted animations for the character so I begun creating them |  |  |  | As a designer I wanted animations for the character so I begun creating them | As a designer I wanted animations for the character so I begun creating them | As a Investor I want a working version of the product so that I can see what has been done
| As a visionary I want Enemies Concepts because it will give a general idea of the enemy apperance | As a Visionary I want a Character Concept because I can then see the character becoming real | As a Player I want a moving player because then I can move around the world | As a player I want the enemies to move because I want a challenge in the game |  |  |  | As a designer I designed projectiles for the boss so that he would have something to fire | As a player I needed a way to change ammo type so that I could use all the different types
As a player I want to be able to attack because I need a way to kill the enemies
Key
Completed On Time
Completed Early
Completed Late